## Schedule
Day | Date | Status | Resposible | Notes
Monday | 2015-07-20 | QA - Internal | Nancy and Team
Tuesday | 2015-07-21 | Development - Molly's latest edits | Andy
Wednesday | 2015-07-22 | QA - Internal | Tim and Team
Thursday | 2015-07-23 | QA - Client Review | Molly & David
Friday | 2015-07-24 | QA - Client Review | Molly & David | Schedule Meeting
Monday | 2015-07-27 | QA - Client Review | City & Event Managers
Tuesday | 2015-07-28 | QA - Client Review | City & Event Managers
Wednesday | 2015-07-29 | Feedback review: Approval/Denial of change requests | Full Team | Schedule Meeting
Thursday | 2015-07-30 | Development - Final Edits
Friday | 2015-07-31 | Development - Final Edits
Saturday | 2015-08-01 | Final QA and Go Live | BCG
| 8/3/2015 - 8/14/2015 | Live
Monday | 2015-08-17 | Complie feedback and final changes | Evenergy
Tuesday | 2015-08-18 | Feedback review: Approval/Denial of change requests | Full Team | Schedule Meeting
Wednesday | 2015-08-19 | Development - Final Changes | BCG
Thursday | 2015-08-20 | Development - Final Changes | BCG
Friday | 2015-08-21 | Development & Final QA | BCG
Phase III anyone?

## Edits
Item # | Category | Task | Details | Assigned To | Estimated Hrs To Complete | Assigned Date | Due Date | QA'd | Completed | Priority Level
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
Note on K1: scale of 1 to 3. 1 = most important. 3 = least important